MAPP RFP Demo Readiness

28 October 2026

Up to MVP go-live (RFP Phases 1 and 2, 17 rows), about 60% is done. We can take it to about 65% without Shell; the last 35% needs Shell. The product build itself is 86% done and can reach 100% without Shell.

| Area | Rows | Done today | Without Shell | Needs Shell |
| --- | --- | --- | --- | --- |
| Phase 1: foundation and design | 6 | 58% | 58% | 42% |
| Phase 2: product build | 7 | 86% | 100% | — |
| Phase 2: configuration, migration, UAT, go-live | 4 | 13% | 13% | 87% |
| Total | 17 | 59% | 65% | 35% |

What is there: ready to demo

Planning: plans, campaigns, initiatives, activities and line items; yearly, quarterly and monthly views; copy last year's plan

Budgets: monthly phasing, global budgets split to markets, exchange rates in local currency and USD

Approvals: multi-level, auto-approval under a threshold, delegation, missing data blocks submission

Access: market vs global, edit vs view vs approve

Settings: attributes, currencies, roles, teams and workflows, run by Shell admins

Purchase request to PO, on a simulated GSAP

What we can do without Shell

SP&A view and BCPIR marker, as defined in Shell's spec 006

Excel import and bulk edit of plans

Executive and regional dashboards; export to PowerPoint and PDF

Overspend control (hard stop or warning), with a default rule Shell can change

Finish the open screens: role-aware buttons, attribute filters, field help, approvers' roles from Settings

The 12 missing end-to-end tests

What we cannot do without Shell

| Item | Needs from Shell |
| --- | --- |
| Requirements and operating model sign-off | Answers to 41 open questions; sign-off on 58 defaults |
| Mobility and Lubricants configuration | Real markets, users, roles and option lists |
| Hive9 data migration | Hive9 data dump, mapping sign-off, cut-over rules |
| Deployment and single sign-on | Azure@Shell environments; Entra ID app registration |
| UAT and go-live | Business SMEs and UAT time |
| GSAP integration (after Nucleus, ~Mar 2027) | Interface specs and sample files |

Scoring: covered = 1, mostly = 0.75, partly = 0.5, not = 0 per RFP row; vendor contracting left out. An estimate, not a measurement.